# CITY OF REDONDO BEACH STRATEGIC PLAN   

# THREE-YEAR GOALS

# SIX-MONTH OBJECTIVES

# January 27, 2022 – July 27, 2022

CM= City Manager   ATCM=Assistant to City Manager   CD=Community Development   CS=Community Services   FD=Fire Department   FS=Financial Services   HR=Human Resources   IT=Information Technology   LIB=Library   PD=Police Department   PW=Public Works   WED=Waterfront and Economic Development   CA=City Attorney   CC=City Clerk   CT=City Treasurer

| A GOAL 1: Modernize the City’s Communication Systems |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # WHEN | ## WHO | ### OBJECTIVES | STATUS |  |  | COMMENTS |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By July 27, 2022 | ATCM, CM | City Branding: Identify and procure resources needed to facilitate rebranding effort; overall aim is to capture the full diversity and flavor of the City. |  |  |  |  |
| 2. By July 1, 2022 (if current vendor is selected; by 10/1 if new vendor) | IT & ATCM | City Website: Establish requirements and sign a contract with vendor to rebuild current website. Make it more appealing, more user friendly, simpler, searchable, incorporating modern, responsive design customized to Redondo Beach, with a good CMS and strong SEO plan to support it. Website should have council member pages that are editable by council members and a clear path for people who want to do business with the City. |  |  |  |  |
| 3. By July 27, 2022 | ATCM & CM working with advisory group | City Communications Plan: Update the City’s communications plan. Include brand alignment, different communications platforms, social media, two-way communications, surveying, and public input gathering. |  |  |  |  |
| 4. By July 5, 2022 | ATCM, PW (CIP), FS & IT | Internal Communications: Provide report to Council on gaps in internal communications with potential solutions. Goal is to upgrade City’s internal communications to include project status and budget reports. |  |  |  |  |
| 5. By April 5, 2022 | CM, CA & CC | City Charter Review: Provide report to Council on options to establish City Charter Review Advisory Committee. First meeting to be held by June 5. |  |  |  |  |
| 6. By July 26, 2022 | ATCM, CA & CC | Sunshine Policy: Review policies of other Cities, summarize the City’s options and report to Council. |  |  |  |  |
| 7. By July 26, 2022 | ATCM & CS | Volunteer Coordination: Determine a plan for coordinating City’s various volunteer groups and report to Council. |  |  |  |  |

| A GOAL 2: Vitalize Core Commercial Areas of the City |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # WHEN | ## WHO | ### OBJECTIVES | STATUS |  |  | COMMENTS |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By July 1, 2022 | CD & WED | Artesia AACAP Implementation: Consider environmental analysis and introduce ordinance to amend municipal code for Artesia FAR and other changes recommended in the AACAP. |  |  |  |  |
| 2. By Sept. 1, 2022 | CD & WED | Artesia Parking: Consider environmental analysis and introduce ordinance to amend municipal code for Artesia parking regulations related to the AACAP. |  |  |  |  |
| 3. By April 5, 2022 | PW & IT | Broadband: Explore and report to Council on grant opportunities related to middle-mile broadband expansion to core commercial areas. |  |  |  |  |
| 4. By July 1, 2022 | CD & CA | Finalize Cannabis Ordinance |  |  |  |  |
| 5. By May 3, 2022 | CS | Mural Ordinance: Report on mural ordinance options, available sites. |  |  |  |  |
| 6. By May 3, 2022 | FS & WED | Business/Parking Improvement Districts: Report to Council on options for business and/or parking district formation. |  |  |  |  |
| 7. By June 1, 2022 | WED & ATCM | International Boardwalk: Create a matching storefront improvement program for International Boardwalk, working with King Harbor and Pier associations. |  |  |  |  |
| 8. By July 26, 2022 | WED, CD & CM | Business Concierge Program: Report to Council on potential program to help expedite business development in the City. |  |  |  |  |
| 9. By May 15, 2022 | ATCM & PW | EV Charger Expansion: Seek additional federal grant funding for EV chargers on commercial corridors. |  |  |  |  |
| 10. By April 5, 2022 | CD & CA | Administrative Review and Anti-Blight Ordinance: Bring draft ordinance concepts to Council for consideration |  |  |  |  |
| 11. By March 15, 2022 | CD & CA | Design Review: Bring draft language to Council to amend administrative design review and planning commission design review procedures. |  |  |  |  |

| GOAL 3: Increase Environmental Sustainability |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # WHEN | ## WHO | ### OBJECTIVES | STATUS |  |  | COMMENTS |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By June 1, 2022 | ATCM & PW | Edison Right-Of-Way License: Following execution of license, develop conceptual plan for beautification and habitat restoration on Edison right-of-way west of PCH |  |  |  |  |
| 2. By Feb. 15, 2022 | PW | Bicycle Master Plan: Provide an update on the status of master bicycle plan implementation. |  |  |  |  |
| 3. By June 7, 2022 | PW | Multi-Modal Plan: Discuss and decide on measurable goals for implementation of existing bicycle master plan; review local travel network concepts and report to Council. |  |  |  |  |
| 4 By March 15, 2022 | PW & CA | Tree Ordinance: Summarize feedback from Commissioners, report to Council and get direction from Council on development of ordinance. |  |  |  |  |
| 5. By July 5, 2022 | PW | Water Quality: Review the EWMP plan and report to council on next steps for implementation. |  |  |  |  |
| 6. By July 26, 2022 | CD | Bike Racks: Review options for bike rack designs and expanded installation on commercial properties and report to Council. |  |  |  |  |
| 7. By June 21, 2022 | CD | Tree Plantings: Provide a Budget Response Report on options for planting trees in available city-controlled planting sites. |  |  |  |  |
| 8. By April 19, 2022 | PD (Code Enforcement) | Plastic Waste: Report on current enforcement of plastic waste laws and ways to enhance compliance. |  |  |  |  |
| 9. By July 26, 2022 | WED | White Sea Bass Program: Report to Council on options to re-establish White Sea Bass program in King Harbor. |  |  |  |  |
| 10. By June 7, 2022 | ATCM & CC | Environmental Advisory Body: Report on options for advising the City on environmental issues through either expansion of an existing commission or creation of a new commission. |  |  |  |  |

| A GOAL 4: Invest in the City’s Infrastructure |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # WHEN | ## WHO | ### OBJECTIVES | STATUS |  |  | COMMENTS |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By February 15, 2022 | FS, PW & CM | Infrastructure Bond: Explore and provide report on bond process and possible uses, including renovations to key civic buildings; followed by report on transactional milestones |  |  |  |  |
| 2. By June 7, 2022 | PW & CS | Wilderness Park Ponds: Develop plan for maintenance of upper pond; assess lower pond and plan for restoration and reconstruction, and report to Council. |  |  |  |  |
| 3. By May 3, 2022 | CS, WED & PW | Seaside Lagoon: Prepare RFP for selecting an aquatics design firm to redesign and rehabilitate the Lagoon. |  |  |  |  |
| 4. By June 7, 2022 | CS & ATCM | Veterans Park Library: Identify and present to Council options for a new facility use plan and solicit prospective operators. |  |  |  |  |
| 5. By March 15, 2022 | PW | Dominguez Park and Dog Park Improvements: Report to Council on scope of work and timetable for implementation. |  |  |  |  |
| 6. By June 14, 2022 | PW | Grant Ave. Repaving: Provide Budget Response Report on funding options. |  |  |  |  |
| 7. By April 5, 2022 | PW working with West Basin | Recycled Water: Develop a plan to connect recycled water (purple pipe) to Manhattan Beach Blvd., Anderson Park, and North Redondo Beach bike path. |  |  |  |  |
| 8. By March 15, 2022 | CS & PW | Aviation Park: Provide a report on short- and long-term improvements and additional amenities for the following: painting of the gym, concrete work, and potential aquatic center. |  |  |  |  |
| 9. By March 15, 2022 | PW | Riviera Village Mobility Assessment: Report to Council on Riviera Village mobility assessment focusing on pedestrian movement. |  |  |  |  |
| 10. By May 17, 2022 | WED | Sea Level Rise: Report to Council on status of sea level rise impacts with assessment, next steps, and possible mitigation funding sources. |  |  |  |  |
| 11. By April 5, 2022 | CD & PW | Riviera Village Outdoor Dining Parklets: Report to Council on Coastal Commission response regarding long term program implementation. |  |  |  |  |

| A GOAL 5: Maintain a High Level of Public Safety |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # WHEN | ## WHO | ### OBJECTIVES | STATUS |  |  | COMMENTS |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By March 1, 2022 | FD | Fire Department Assessment: Deliver report to Council on Fire Dept. assessment. |  |  |  |  |
| 2. By July 26, 2022 | PW & ATCM | Expand Streets For All Program: Re-engage with Health District and explore grant opportunities; report to Council. |  |  |  |  |
| 3. By July 26, 2022 | PD & PW | Speed Limits: Report to Council on when the City could implement reduced speed limits under AB43. |  |  |  |  |
| 4. By May 10, 2022 | CA | Enhanced Response to Homelessness: Report to Council on options for enhanced response to help address homelessness, including improved coordination with the County. |  |  |  |  |
| 5. By Feb. 15, 2022 | PD & PW | Crime and Car Accident Report for 2021: Report to Council on crime statistics and vehicle accident data, including car and pedestrian collisions, and trends. |  |  |  |  |
| 6. By Feb. 15, 2022 | PD | Waterfront Safety: Provide Budget Response Report to Council on enhancing safety at the waterfront, with options for operational and capital improvements. |  |  |  |  |

| A GOAL 6: Enhance the Delivery of City Services |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # WHEN | ## WHO | ### OBJECTIVES | STATUS |  |  | COMMENTS |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By June 7, 2022 | LIB, PW & IT | Library Self-Serve Hours: Report to Council on benefits and feasibility of library self-serve program at north branch. |  |  |  |  |
| 2. By May 17, 2022 | CM, PW & HR | Public Works Employee Retention: Develop a plan to attract and retain public works employees and present to Council. |  |  |  |  |
| 3. By July 5, 2022 | ATCM & IT | Transition More City Services to Online: Provide a report to Council on options to continue and expand the plan to transition public-facing City services online. |  |  |  |  |
| 4. By July 26, 2022 | CM, CA & CC | Code of Conduct: Develop a code of conduct for Commissioners and present it to Council for consideration of approval. |  |  |  |  |
| 5. By March 15, 2022 | CM, CA & CC | Campaign Finance Reform: Report to Council on possible updates to campaign finance ordinance and enforcement options. |  |  |  |  |
| 6. By April 5, 2022 | FS, CT & CC | Moss Adams Review: Report to Council on status of Moss Adams findings and next steps. |  |  |  |  |
| 7. By April 19, 2022 | PW | Traffic Calming Policies: Report to City Council on policy changes that would accelerate the implementation of traffic calming improvements. |  |  |  |  |
| 8. By June 7, 2022 | PW | Digital Speed Limit Feedback Signs: Provide a Budget Response Report on cost to install radar feedback signs and collect data. |  |  |  |  |